## SCRUM Tickets
Key | Summary | IssueType | Status | Priority | Assignee | Labels | Sprint | EpicLink | StoryPoints | Description | AcceptanceCriteria | Created | Updated
SCRUM-4 | Subtask 2.1 | Subtask | Idea | [8 empty] | 2026-08-13T17:05:22.889+0700 | 2026-08-13T17:05:23.220+0700
SCRUM-5 | [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | Epic | Idea | Medium |  | phase-1, role-dev, role-po |  |  |  | Role focus: Product Owner + Developer Goal: the ugliest possible version of the browse → basket → checkout → order flow, deployed and demoable. No meaningful test coverage or hardening yet — this phase proves the path exists end to end. Scope: parties (stubbed identity + resolved tenant context), products, baskets, orders services; gateway + BFF routing; minimal React SPA; single-command local deploy. Part of the Ecommerce SDLC Practice Platform roadmap (docs/roadmap.md). |  | 2026-08-13T20:22:37.864+0700 | 2026-08-13T20:22:38.007+0700
SCRUM-6 | [Phase 2] Contracts and Test-First Retrofit | Epic | Idea | Medium |  | phase-2, role-dev, role-qa |  |  |  | Role focus: Developer + QA Goal: retrofit the principles the Phase 1 skeleton skipped — contracts before code, red-green-refactor, real integration tests against real dependencies. Scope: OpenAPI specs + generated clients, event schemas, TDD for basket/order logic, Testcontainers integration tests, consumer-driven contract tests, SonarQube quality gate as a merge blocker. Part of the Ecommerce SDLC Practice Platform roadmap (docs/roadmap.md). Depends on Phase 1 (WALK-1) being walking, not necessarily done. |  | 2026-08-13T20:22:44.889+0700 | 2026-08-13T20:22:44.941+0700
SCRUM-7 | [Phase 3] Real Auth, Deny-by-Default, Full Observability | Epic | Idea | Medium |  | phase-3, role-devops |  |  |  | Role focus: DevOps Goal: replace Phase 1/2 stubs with the real security and observability posture the platform constitution requires. Scope: identity server + real token issuance, deny-by-default authorization on every endpoint/handler, OpenTelemetry traces/metrics/logs via shared ServiceDefaults to Elastic, correlation ID propagation edge-to-frontend, secrets via cluster secret store, liveness/readiness probes. Part of the Ecommerce SDLC Practice Platform roadmap (docs/roadmap.md). Depends on Phase 2 (CONTRACT-2) being walking, not necessarily done. |  | 2026-08-13T20:22:52.379+0700 | 2026-08-13T20:22:52.448+0700
SCRUM-8 | [Phase 4] Budgets, Timeouts, and Failure Injection | Epic | Idea | Medium |  | phase-4, role-sre |  |  |  | Role focus: SRE Goal: turn the constitution's performance budgets from aspiration into something measured and enforced. Scope: per-service SLOs, timeout/retry/circuit-breaker policies on every outbound call, outbox verification, load/performance testing against p95/p99 budgets, N+1/pagination audit, chaos exercise (pod kill / latency injection). Part of the Ecommerce SDLC Practice Platform roadmap (docs/roadmap.md). Depends on Phase 3 (SECURE-3) being walking, not necessarily done. |  | 2026-08-13T20:22:59.164+0700 | 2026-08-13T20:22:59.253+0700
SCRUM-9 | [Phase 5] Incident Response and Error-Budget Policy | Epic | Idea | Medium |  | phase-5, role-sre |  |  |  | Role focus: SRE Goal: practice the parts of SRE that only show up once something is live — incidents, error budgets, safe rollback. Scope: error-budget policy + alerting thresholds, a deliberately triggered incident with real on-call response, blameless postmortem, toggle-gated rollback practice, quarterly-style constitutional compliance review. Part of the Ecommerce SDLC Practice Platform roadmap (docs/roadmap.md). Depends on Phase 4 (RESILIENCE-4) being walking, not necessarily done. |  | 2026-08-13T20:23:05.658+0700 | 2026-08-13T20:23:05.705+0700
SCRUM-10 | [WALK-1] Scope the thin-slice one-pager | Story | Done | Highest | dev2 | owner-dev2, phase-1, role-po, sprint-1 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 1 | As the Product Owner, I want a one-page scope for the thin slice so that the walking skeleton has a fixed, minimal target instead of growing scope mid-build. Scope locked to: one product, one basket, one order, one hardcoded tenant, one fake user. | - Given the one-pager is written, when I read it, then it states exactly which services (parties, products, baskets, orders), which flow steps, and which tenant/user are in scope for Phase 1. - Given the one-pager exists, when I check it against Phase 2+ scope items, then nothing from later phases (real auth, observability, resilience) appears as in-scope. - Given the one-pager is complete, when I share it with "QA/DevOps/SRE" (myself, later), then the demo definition of done is unambiguous: one order placed end to end. Test Scenarios - Review one-pager against roadmap.md — confirm scope matches Phase 1 section exactly. - Walk through the one-pager and try to find an ambiguous requirement — none should exist. | 2026-08-13T20:23:23.213+0700 | 2026-08-18T21:25:18.052+0700
SCRUM-11 | [WALK-1] Scaffold parties/products/baskets/orders service shells | Story | Done | Highest | dev1 | owner-dev1, phase-1, role-dev, sprint-0 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 8 | As the Developer, I want scaffolded service shells for parties, products, baskets, and orders using vertical-slice structure so that each service has its own owned datastore and a place to add the thin-slice logic. | - Given a fresh clone of the repo, when I run each service, then it starts independently and exposes a health endpoint. - Given the four services exist, when I inspect their persistence, then each owns its own database/schema — none read or write another service's tables (Principle I). - Given the vertical-slice default from the constitution, when I look at the folder structure, then feature code is organized by slice, not by technical layer, unless a documented invariant justifies otherwise. Test Scenarios - Start each of the 4 services independently — each boots without depending on the others being up. - Attempt a cross-service DB query — confirm it is architecturally impossible (separate connection strings/schemas). - Hit each service's health endpoint — expect 200 OK. | 2026-08-13T20:23:53.665+0700 | 2026-08-15T08:59:34.839+0700
SCRUM-12 | [WALK-1] Stub identity with a resolved tenant context | Story | Done | Highest | dev3 | owner-dev3, phase-1, role-dev, sprint-0 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 3 | As the Developer, I want a single fake authenticated user whose request always carries a resolved tenant context so that no code path can reach persistence without one, even before the real identity server exists (Principle V). | - Given a request enters at the gateway, when it is forwarded downstream, then it carries an explicit tenant identifier through gateway → BFF → services. - Given a service handler is invoked, when it touches persistence, then the tenant identifier is required to resolve the connection — there is no default/fallback tenant. - Given the tenant source is hardcoded for Phase 1, when Phase 3 replaces it with real token claims, then only the resolution source changes, not the propagation mechanism. Test Scenarios - Trace a single request end to end and confirm the tenant ID is visible in logs at every hop. - Attempt to call a persistence method with no tenant context — confirm it throws/fails rather than silently defaulting. - Grep the codebase for any repository/DB call that does not require a tenant parameter — expect zero results. | 2026-08-13T20:24:00.166+0700 | 2026-08-16T12:15:26.159+0700
SCRUM-13 | [WALK-1] Wire gateway → BFF routing for the three services | Story | Done | High | dev3 | owner-dev1, phase-1, role-dev, sprint-0 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 5 | As the Developer, I want the API gateway and BFF wired to route to products, baskets, and orders so that the frontend has a single backend surface to call, per the platform's edge architecture. | - Given the SPA calls the BFF, when the BFF needs product/basket/order data, then it aggregates from the underlying services rather than the SPA calling them directly. - Given a request hits the gateway, when it is routed, then it reaches the correct downstream service without the client knowing service topology. - Given the BFF aggregates calls, when I inspect its code, then it contains no business logic beyond aggregation/shaping. Test Scenarios - Call the BFF's product-listing route — confirm it proxies to the products service and returns shaped data. - Attempt to call a microservice directly from the SPA's network tab — confirm the SPA never does this (BFF-only access). - Kill the products service — confirm the gateway/BFF returns a clear error rather than hanging (precursor check for Phase 4 resilience work). | 2026-08-13T20:24:06.260+0700 | 2026-08-15T17:46:17.071+0700
SCRUM-14 | [WALK-1] Minimal React SPA: browse, basket, checkout, confirmation | Story | Done | High | dev2 | owner-dev2, phase-1, role-dev, sprint-0 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 8 | As a shopper, I want to browse a product, add it to my basket, and check out so that I receive an order confirmation, exercising the full thin slice from the UI. | - Given I open the SPA, when the page loads, then I see at least one product listed. - Given I add the product to my basket, when I view the basket, then it reflects the item and quantity correctly. - Given I click checkout, when the order is placed, then I see a confirmation screen referencing the created order. - Given the SPA is React + TypeScript + Vite, when I inspect the code, then TypeScript strict mode is on with no unjustified any. Test Scenarios - Manual walkthrough: browse → add to basket → checkout → confirmation, no errors in console. - Refresh mid-basket — confirm basket state behavior is defined (even if "resets" for Phase 1, it should be an intentional choice, not undefined behavior). - Attempt checkout with an empty basket — confirm the UI blocks it rather than sending a broken request. | 2026-08-13T20:24:12.079+0700 | 2026-08-16T22:08:53.424+0700
SCRUM-15 | [WALK-1] One-command local run with real containers | Story | Done | High | Dev Ops | owner-devops, phase-1, role-devops, sprint-0 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 5 | As the DevOps-hat-wearer, I want the entire skeleton runnable locally with one command so that local development matches the platform's "runnable locally with real dependencies via containers" constraint from day one. | - Given a clean machine with Docker installed, when I run the single documented command, then all services, SQL Server, Redis, and RabbitMQ start and become healthy. - Given the stack is up, when I open the SPA URL, then the app is fully functional without any additional manual steps. - Given the command is documented, when a new contributor (future me) follows it, then no undocumented manual steps are required. Test Scenarios - From a clean checkout, run the one command and time how long until the SPA is usable. - Stop and restart the stack — confirm it comes back up cleanly (no orphaned containers/ports). - Intentionally omit a dependency container — confirm the failure is obvious, not silent. | 2026-08-13T20:24:18.121+0700 | 2026-08-18T21:10:55.943+0700
SCRUM-16 | [WALK-1] Demo: place one order end to end | Story | Done | Highest | QA | owner-qa, phase-1, role-po, role-qa, sprint-0 | SCRUM Sprint 0 (closed) | SCRUM-5 - [Phase 1] Walking Skeleton: Browse → Basket → Checkout → Order | 2 | As the Product Owner, I want to watch one order get placed end to end on the deployed skeleton so that Phase 1 has an unambiguous, demoable definition of done. | - Given the skeleton is deployed (locally or to K8s), when I perform the browse → basket → checkout flow, then an order record is persisted in the orders service. - Given the order is placed, when I query the orders service directly, then the order's tenant ID matches the resolved tenant context from the request. - Given the demo is run, when I record it, then it becomes the reference artifact proving Phase 1 exit criteria are met. Test Scenarios - Run the full demo live and narrate each hop (SPA → BFF → gateway → services) — confirm no manual intervention is needed mid-flow. - Re-run the demo a second time — confirm it's repeatable, not a one-off that only worked once. - Check the persisted order record's tenant field — confirm it is non-null and correct. | 2026-08-13T20:24:24.305+0700 | 2026-08-20T18:32:18.904+0700
SCRUM-17 | [CONTRACT-2] OpenAPI specs for BFF routes + generated clients | Story | Done | High | dev2 | owner-dev2, phase-2, role-dev, sprint-1 | SCRUM Sprint 1 (future) | SCRUM-6 - [Phase 2] Contracts and Test-First Retrofit | 5 | As the Developer, I want OpenAPI specs written for the products/baskets/orders BFF routes, with client code generated from them, so that the contract is the source of truth and hand-written client drift is impossible (Principle II). | - Given a BFF route exists, when I look for its contract, then an OpenAPI spec for it exists and was written before the route's implementation was finalized. - Given the OpenAPI spec changes, when I regenerate the client, then the SPA's API client is fully generated — no hand-written HTTP calls remain. - Given a consumer receives a response, when it contains an unknown field, then the generated client does not break (tolerant reader). Test Scenarios - Diff the generated client against the OpenAPI spec — confirm they match exactly (no manual edits to generated files). - Add an unused field to a mock response — confirm the SPA doesn't crash. - Search the SPA codebase for raw fetch/axios calls to BFF endpoints — expect none outside the generated client. | 2026-08-13T20:24:45.111+0700 | 2026-08-22T13:43:12.173+0700
SCRUM-18 | [CONTRACT-2] Versioned event schemas: OrderPlaced, BasketCheckedOut | Story | Done | High | dev3 | owner-dev3, phase-2, role-dev, sprint-1 | SCRUM Sprint 1 (future) | SCRUM-6 - [Phase 2] Contracts and Test-First Retrofit | 3 | As the Developer, I want versioned event schemas for OrderPlaced and BasketCheckedOut in a shared contracts location so that future consumers can integrate against a stable, evolvable contract (Principle II). | - Given an event schema is defined, when I look at its location, then it lives in the shared contracts location, not inline in the publishing service. - Given a schema changes in a breaking way, when I ship it, then it carries a new explicit version and the previous version keeps working for a documented deprecation window. - Given a consumer receives an event, when it contains unknown fields, then it does not fail deserialization. Test Scenarios - Publish an OrderPlaced event and confirm it validates against the published schema. - Add a new required field to the schema without versioning it — confirm this is caught (should fail a contract-compat check). - Simulate an old consumer reading a new-version event — confirm no crash on unknown fields. | 2026-08-13T20:24:51.281+0700 | 2026-08-22T14:20:29.333+0700
SCRUM-19 | [CONTRACT-2] Retrofit TDD for basket pricing and order creation | Story | Done | High | dev1 | owner-dev1, phase-2, role-dev, role-qa, sprint-1 | SCRUM Sprint 1 (future) | SCRUM-6 - [Phase 2] Contracts and Test-First Retrofit | 8 | As the Developer, I want basket pricing and order-creation logic rebuilt test-first so that Phase 1's untested shortcuts are replaced with Red-Green-Refactor discipline (Principle III, non-negotiable). | - Given a new piece of pricing/order logic is touched, when I commit it, then a failing test preceded the implementation that made it pass (visible in commit history). - Given basket pricing logic exists, when unit tests run, then edge cases (zero quantity, price change mid-session, duplicate line items) are covered. - Given order-creation logic exists, when unit tests run, then invalid state transitions are rejected with tests proving it. Test Scenarios - Review commit history for pricing/order-creation changes — confirm test commits precede or accompany implementation commits, not follow days later. - Run the unit test suite — confirm it fails if pricing logic is reverted to Phase 1 behavior. - Attempt to create an order from an empty basket at the domain layer — confirm it's rejected with a test asserting this. | 2026-08-13T20:24:57.249+0700 | 2026-08-22T14:53:20.320+0700
SCRUM-20 | [CONTRACT-2] Integration tests via Testcontainers (SQL Server, Redis, RabbitMQ) | Story | Done | High | QA | owner-qa, phase-2, role-qa, sprint-1 | SCRUM Sprint 1 (future) | SCRUM-6 - [Phase 2] Contracts and Test-First Retrofit | 8 | As QA, I want integration tests running against real SQL Server, Redis, and RabbitMQ via Testcontainers so that the suite catches what in-memory fakes would hide (Principle III). | - Given the integration test suite runs, when it starts, then it spins up real containers for SQL Server, Redis, and RabbitMQ rather than in-memory substitutes. - Given a basket is checked out, when the integration test runs, then it verifies the actual persisted row and the actual published message, not a mock's recorded call. - Given the suite runs in CI, when a container fails to become healthy, then the test run fails loudly rather than silently skipping. Test Scenarios - Run the integration suite locally and confirm containers are visible in docker ps during the run. - Introduce a real SQL constraint violation — confirm the integration test catches it (an in-memory provider would not). - Kill RabbitMQ mid-test — confirm the test fails rather than hanging indefinitely (ties to Phase 4 timeout work, but the test itself must not hang). | 2026-08-13T20:25:03.148+0700 | 2026-08-22T15:39:00.707+0700
SCRUM-21 | [CONTRACT-2] Consumer-driven contract tests across BFF/service boundaries | Story | Done | Medium | QA | owner-qa, phase-2, role-qa, sprint-2 | SCRUM Sprint 1 (future) | SCRUM-6 - [Phase 2] Contracts and Test-First Retrofit | 5 | As QA, I want consumer-driven contract tests on every HTTP and event boundary so that a producer breaking a published contract fails its own build, not a downstream consumer's (Principle III). | - Given the BFF consumes the products/baskets/orders services, when a contract test suite runs, then it verifies the producer's real response against the consumer's expectations. - Given a producer changes a response shape in a breaking way, when its build runs, then the contract test fails before merge. - Given all boundaries in the thin slice, when I list them, then every one (BFF↔products, BFF↔baskets, BFF↔orders, event producer↔consumer) has a contract test. Test Scenarios - Break a field name in the products service response — confirm the products service's own build fails the contract test. - List all HTTP/event boundaries in the slice and cross-check each has a corresponding contract test file. - Remove a contract test intentionally — confirm CI catches the coverage gap (or note this as a manual review item if no automated gate exists yet). | 2026-08-13T20:25:09.363+0700 | 2026-08-22T20:11:43.441+0700
SCRUM-22 | [CONTRACT-2] Wire SonarQube quality gate as a merge blocker | Story | Done | Medium | Dev Ops | owner-devops, phase-2, role-devops, sprint-0 | SCRUM Sprint 1 (future) | SCRUM-6 - [Phase 2] Contracts and Test-First Retrofit | 3 | As DevOps, I want the SonarQube quality gate wired into the build and enforced as a merge blocker so that coverage and code-quality standards are machine-enforced, not reviewed by eye (Development Workflow & Quality Gates). | - Given a PR is opened, when the pipeline runs, then it executes build → unit tests → integration tests → contract tests → SonarQube gate in sequence. - Given the SonarQube gate fails, when I try to merge, then the merge is blocked with no override path. - Given the gate passes, when I check the PR status, then the quality metrics (coverage, duplication, code smells) are visible on the PR. Test Scenarios - Open a PR that intentionally drops coverage below threshold — confirm merge is blocked. - Attempt to bypass the gate (e.g., admin merge) — confirm this is either disabled or requires explicit, logged justification. - Fix the coverage gap and re-push — confirm the gate re-evaluates and unblocks the PR. | 2026-08-13T20:25:16.231+0700 | 2026-09-01T17:24:15.771+0700
SCRUM-23 | [SECURE-3] Stand up identity server, replace stubbed auth | Story | Done | Highest | Dev Ops | owner-devops, phase-3, role-devops, sprint-1 | SCRUM Sprint 2 (future) | SCRUM-7 - [Phase 3] Real Auth, Deny-by-Default, Full Observability | 8 | As DevOps, I want a real identity server issuing tokens so that Phase 1's fake user is replaced with genuine authentication, per the platform's centralized identity model. | - Given the identity server is running, when a user logs in, then it issues a token containing verified identity and tenant claims. - Given a request carries a token, when it reaches the gateway, then the token is validated at the gateway AND independently at each service — the gateway is not a trust boundary services rely on. - Given the Phase 1 tenant-resolution stub, when this story completes, then only the resolution source changed (token claim instead of hardcode) — propagation mechanism is untouched. Test Scenarios - Log in through the identity server and confirm a valid JWT/token is issued with tenant claim. - Send a request with a tampered token directly to a downstream service (bypassing the gateway) — confirm the service independently rejects it. - Send a request with an expired token — confirm it's rejected with a clear 401, not a silent failure. | 2026-08-13T20:25:32.476+0700 | 2026-09-02T14:32:33.179+0700
SCRUM-24 | [SECURE-3] Deny-by-default authorization on every endpoint/handler | Story | Done | Highest | dev2 | owner-dev2, phase-3, role-devops, sprint-2 | SCRUM Sprint 2 (future) | SCRUM-7 - [Phase 3] Real Auth, Deny-by-Default, Full Observability | 5 | As DevOps, I want every endpoint and message handler to declare an explicit authorization policy so that nothing is reachable by accident (Principle VI). | - Given any HTTP endpoint or message handler in the slice, when I inspect it, then it has an explicit authorization policy attached. - Given an endpoint is added without an authorization decision, when the build runs, then the build or review fails — there is no silent-allow default. - Given client-side validation exists in the SPA, when I test it, then server-side validation independently enforces the same rules (client-side is UX only). Test Scenarios - Grep all controllers/handlers for missing [Authorize]-equivalent attributes — expect zero. - Call an endpoint with a token lacking the required policy claim — confirm 403, not 200. - Bypass the SPA's client-side validation (e.g., via direct API call) — confirm the server independently rejects invalid input. | 2026-08-13T20:25:38.717+0700 | 2026-09-03T19:31:27.444+0700
SCRUM-25 | [SECURE-3] OTel traces/metrics/logs via ServiceDefaults to Elastic | Story | Done | High | dev1 | owner-dev3, phase-3, role-sre, sprint-2 | SCRUM Sprint 2 (future) | SCRUM-7 - [Phase 3] Real Auth, Deny-by-Default, Full Observability | 5 | As the SRE-hat-wearer, I want every service emitting OpenTelemetry traces, metrics, and structured logs through a shared ServiceDefaults component so that observability is consistent, not hand-rolled per service (Principle VII). | - Given a service starts, when it initializes, then it wires OTel via the shared ServiceDefaults component, not a bespoke per-service setup. - Given a request flows through the slice, when I query Elastic, then I can see traces, metrics, and structured logs for every hop. - Given a log statement is written, when I inspect it, then it is structured (not an interpolated string) and carries service, tenant, and correlation identifiers. Test Scenarios - Place one order and find its full trace across all 4 services in Elastic/Kibana. - Grep the codebase for string-interpolated log calls — expect none. - Remove ServiceDefaults from one service temporarily — confirm it loses telemetry, proving the shared component is actually load-bearing. | 2026-08-13T20:25:43.410+0700 | 2026-09-06T15:54:38.240+0700
SCRUM-26 | [SECURE-3] Correlation ID propagation edge-to-frontend | Story | Done | High | dev3 | owner-dev3, phase-3, role-sre, sprint-2 | SCRUM Sprint 2 (future) | SCRUM-7 - [Phase 3] Real Auth, Deny-by-Default, Full Observability | 3 | As the SRE-hat-wearer, I want a correlation ID generated at the edge and propagated across every synchronous call, message, and through the frontend so that any failure is traceable across service boundaries (Principle VII). | - Given a request enters at the gateway, when a correlation ID is not already present, then one is generated there. - Given the correlation ID exists, when the request/event travels through BFF, services, and RabbitMQ messages, then it is present at every hop's logs. - Given the SPA makes a request, when I inspect the network tab, then the correlation ID is visible client-side too, not just server-side. Test Scenarios - Place an order and grep Elastic logs across all services for a single correlation ID — confirm it appears at every hop, including the async OrderPlaced event consumer. - Send a request without a pre-existing correlation ID — confirm the gateway generates one. - Send two concurrent requests — confirm their correlation IDs never cross-contaminate in logs. | 2026-08-13T20:25:49.338+0700 | 2026-09-06T11:09:00.057+0700
SCRUM-27 | [SECURE-3] Secrets via cluster secret store, remove hardcoded config | Story | Done | Highest | Dev Ops | owner-devops, phase-3, role-devops, sprint-2 | SCRUM Sprint 2 (future) | SCRUM-7 - [Phase 3] Real Auth, Deny-by-Default, Full Observability | 5 | As DevOps, I want all secrets sourced from the cluster secret store at runtime so that nothing sensitive lives in source, config files, or images (Principle VI). | - Given any service configuration, when I inspect it, then no connection strings, keys, or tokens are hardcoded in source, appsettings files, or Dockerfiles. - Given a service starts in the cluster, when it needs a secret, then it's injected at runtime from the cluster secret store. - Given I scan git history, when I search for credential patterns, then none are found committed anywhere. Test Scenarios - Run a secret-scanning tool (e.g., gitleaks) across the repo history — expect zero findings. - Inspect a built container image's filesystem — confirm no secrets are baked in. - Rotate a secret in the cluster store without redeploying — confirm the service picks it up per the platform's runtime-injection model. | 2026-08-13T20:25:55.295+0700 | 2026-09-07T13:28:51.744+0700
SCRUM-28 | [SECURE-3] Liveness/readiness probes on every service | Story | Done | Medium | Dev Ops | owner-devops, phase-3, role-devops, sprint-2 | SCRUM Sprint 2 (future) | SCRUM-7 - [Phase 3] Real Auth, Deny-by-Default, Full Observability | 2 | As DevOps, I want liveness and readiness probes on every service so that Kubernetes can detect and route around unhealthy instances automatically. | - Given a service is deployed, when I inspect its K8s manifest, then it declares both a liveness and a readiness probe. - Given a service is starting up but not yet ready (e.g., DB connection pending), when traffic is routed, then K8s excludes it until the readiness probe passes. - Given a service hangs or deadlocks, when the liveness probe fails repeatedly, then K8s restarts the pod. Test Scenarios - Deploy a service and watch its pod go from not-ready to ready — confirm no traffic is routed during the not-ready window. - Simulate a hung service (e.g., block its health endpoint) — confirm K8s restarts it after the liveness threshold. - Check all 4 services + gateway + BFF — confirm every one has both probes configured, not just some. | 2026-08-13T20:26:01.520+0700 | 2026-09-06T21:00:34.143+0700
SCRUM-29 | [RESILIENCE-4] Declare per-service SLOs in the service manifest | Story | Done | Medium | Dev Ops | owner-devops, phase-4, role-sre, sprint-3 | SCRUM Sprint 3 (future) | SCRUM-8 - [Phase 4] Budgets, Timeouts, and Failure Injection | 3 | As the SRE-hat-wearer, I want each service to declare its latency, error-rate, and availability SLOs in its manifest so that performance is a stated budget, not an aspiration (Principle VIII). | - Given a service manifest, when I inspect it, then it declares p95/p99 latency, error-rate, and availability targets. - Given no service documents a justified alternative, when I compare its SLOs to the constitution defaults, then they match (BFF read p95≤300ms/p99≤800ms; internal API p95≤150ms/p99≤500ms; 99.9% availability; <0.1% 5xx). - Given the SLOs are declared, when telemetry from Phase 3 is queried, then they are measured continuously, not just documented. Test Scenarios - Pull up each service's manifest and confirm SLOs are present and non-placeholder. - Cross-check declared SLOs against a live dashboard fed by OTel metrics. - Intentionally introduce a slow endpoint — confirm the SLO dashboard shows the budget being consumed. | 2026-08-13T20:26:17.968+0700 | 2026-08-14T10:02:14.305+0700
SCRUM-30 | [RESILIENCE-4] Timeouts, retry, and circuit-breaker on every outbound call | Story | Done | High | dev1 | owner-dev1, phase-4, role-dev, role-sre, sprint-3 | SCRUM Sprint 3 (future) | SCRUM-8 - [Phase 4] Budgets, Timeouts, and Failure Injection | 8 | As the Developer, I want every outbound HTTP or messaging call wrapped with an explicit timeout plus retry/circuit-breaker policy via Microsoft.Extensions.Resilience so that unbounded waits cannot exist anywhere in the system (Principle VIII). | - Given any outbound call (BFF→service, service→service, service→broker), when I inspect its configuration, then it has an explicit timeout. - Given a downstream dependency is slow or down, when the circuit breaker trips, then subsequent calls fail fast instead of queuing up. - Given a transient failure occurs, when the retry policy engages, then it retries with backoff rather than hammering the dependency. Test Scenarios - Grep for outbound HTTP client registrations — confirm every one has a resilience policy attached, none use defaults/unbounded waits. - Kill the products service and hammer the BFF — confirm the circuit breaker opens and requests fail fast after the threshold. - Introduce artificial latency on one dependency — confirm the caller's timeout fires rather than hanging indefinitely. | 2026-08-13T20:26:24.019+0700 | 2026-08-13T22:27:20.710+0700
SCRUM-31 | [RESILIENCE-4] Verify transactional outbox on the order publisher | Story | Done | High | QA | owner-qa, phase-4, role-qa, sprint-3 | SCRUM Sprint 3 (future) | SCRUM-8 - [Phase 4] Budgets, Timeouts, and Failure Injection | 5 | As QA, I want to verify the transactional outbox pattern on the order publisher so that state change and event publication can never diverge, even under crash conditions (Principle IV). | - Given an order is created, when the OrderPlaced event is published, then the order write and the outbox write happen in the same transaction. - Given the process crashes after the DB commit but before the message is sent, when it restarts, then the outbox relay still publishes the event (at-least-once). - Given a consumer receives the same event twice, when it processes it, then the duplicate is a no-op (idempotent consumer). Test Scenarios - Kill the orders service process immediately after commit, before the outbox relay runs — restart and confirm the event still gets published. - Manually replay an OrderPlaced event twice into the consumer — confirm no duplicate side effects. - Force a DB rollback on order creation — confirm no event is published for the failed order. | 2026-08-13T20:26:29.854+0700 | 2026-08-13T22:27:20.907+0700
SCRUM-32 | [RESILIENCE-4] Load/performance test against constitution budgets | Story | Done | Medium | QA | owner-qa, phase-4, role-sre, sprint-4 | SCRUM Sprint 3 (future) | SCRUM-8 - [Phase 4] Budgets, Timeouts, and Failure Injection | 8 | As the SRE-hat-wearer, I want a load test of the critical browse→basket→checkout→order path run against the constitution's stated performance budgets so that a regression is objective, not a red dashboard nobody owns (Principle VIII). | - Given the critical path, when it's load tested, then p95/p99 latency per endpoint class is measured against the declared SLOs from the prior story. - Given a budget is breached, when the test completes, then the run is marked failed, not just "noted." - Given this is a critical user path, when future changes are made, then this performance test is automated and re-runnable, not a one-off manual exercise. Test Scenarios - Run the load test against the current slice and record baseline p95/p99 numbers. - Intentionally introduce a slow DB query, re-run the test — confirm it fails against budget. - Fix the regression and re-run — confirm the test passes again, proving it's a real gate. | 2026-08-13T20:26:36.089+0700 | 2026-09-06T16:50:47.398+0700
SCRUM-33 | [RESILIENCE-4] Audit for N+1 queries, unbounded queries, missing pagination | Story | Done | Medium | dev2 | owner-dev2, phase-4, role-dev, sprint-3 | SCRUM Sprint 3 (future) | SCRUM-8 - [Phase 4] Budgets, Timeouts, and Failure Injection | 5 | As the Developer, I want to audit the slice for N+1 access patterns, unbounded queries, and missing pagination so that these are treated as defects, not future optimization opportunities (Principle VIII). | - Given any collection endpoint (e.g., product listing), when I call it, then it paginates rather than returning an unbounded set. - Given a query loads related data, when I profile it with EF Core logging, then no N+1 pattern is present. - Given a query is bounded, when I check its implementation, then the bound is enforced server-side, not just a client-side page-size hint. Test Scenarios - Seed 500 products and call the listing endpoint without a page parameter — confirm it still returns a bounded page, not all 500. - Enable EF Core query logging and load a basket with multiple items — confirm one query (or a deliberate batch), not one query per item. - Attempt to request an absurdly large page size — confirm the server caps it. | 2026-08-13T20:26:42.676+0700 | 2026-08-13T22:27:21.278+0700
SCRUM-34 | [RESILIENCE-4] Chaos exercise: kill a pod / inject latency | Story | Done | Medium | Dev Ops | owner-devops, phase-4, role-sre, sprint-3 | SCRUM Sprint 3 (future) | SCRUM-8 - [Phase 4] Budgets, Timeouts, and Failure Injection | 5 | As the SRE-hat-wearer, I want to deliberately kill a pod or inject latency into the running system and observe the resilience policies and dashboards react so that the safety nets from earlier stories are proven, not just assumed. | - Given the system is running under light synthetic load, when I kill the basket service's pod, then K8s reschedules it and the circuit breaker/retry policy visibly engages in the BFF. - Given latency is injected into the orders service, when the load exceeds the declared SLO, then the OTel dashboards show the budget being consumed in near real time. - Given the exercise completes, when I write up the outcome, then it either confirms the safety nets worked or becomes a bug ticket if they didn't. Test Scenarios - kubectl delete pod on a running service instance — observe recovery time and whether the BFF degrades gracefully or errors out. - Use a fault-injection tool (or manual sleep injection) to add 2s latency to one service — confirm the circuit breaker trips per its configured threshold. - Watch the Elastic/OTel dashboard live during the exercise — confirm the SLO burn is visible, not just inferred after the fact. | 2026-08-13T20:26:49.388+0700 | 2026-08-13T22:43:55.480+0700
SCRUM-35 | [OPERATE-5] Define error-budget policy and alerting thresholds | Story | Idea | Low | Dev Ops | owner-devops, phase-5, role-sre, sprint-4 | SCRUM Sprint 4 (future) | SCRUM-9 - [Phase 5] Incident Response and Error-Budget Policy | 3 | As the SRE-hat-wearer, I want an error-budget policy and alerting thresholds tied to the Phase 4 SLOs so that a sustained breach has an actual, defined consequence instead of a red dashboard nobody acts on (Principle VIII). | - Given a service's SLOs, when its error budget is calculated, then the policy defines what "exhausted" means numerically (e.g., % of monthly budget consumed). - Given the error budget is exhausted, when I check the policy, then it states that reliability work takes priority over new feature work for that service until recovery. - Given a budget threshold is crossed, when it happens, then an alert fires — the breach is not discovered by manually checking a dashboard. Test Scenarios - Simulate enough synthetic errors to exhaust a service's monthly error budget — confirm the alert fires at the defined threshold. - Review the written policy — confirm it names who/what stops (feature work) when budget is exhausted. - Confirm the alert routes somewhere I'll actually see it (not a channel nobody watches). | 2026-08-13T20:27:18.340+0700 | 2026-08-14T10:02:25.337+0700
SCRUM-36 | [OPERATE-5] Trigger a real incident and run on-call response | Story | Idea | Low | Dev Ops | owner-devops, phase-5, role-sre, sprint-4 | SCRUM Sprint 4 (future) | SCRUM-9 - [Phase 5] Incident Response and Error-Budget Policy | 5 | As the SRE-hat-wearer, I want to deliberately trigger an incident (bug or outage injection) and run a genuine on-call response so that incident response is rehearsed under real conditions, not just described. | - Given the incident is triggered, when the alert fires, then I follow a real triage flow: detect, assess severity, communicate status, mitigate. - Given the incident is active, when I respond, then I produce a timeline of what was observed and done, with timestamps. - Given the incident is resolved, when I check system state, then service is confirmed restored via telemetry, not just "it looks fine." Test Scenarios - Inject a real failure (e.g., corrupt config, exhaust a connection pool) without pre-announcing the exact cause to future-me. - Time from alert-fire to first mitigation action — record it as a baseline metric. - Confirm the incident timeline captures detection time, mitigation time, and resolution time distinctly. | 2026-08-13T20:27:25.739+0700 | 2026-08-13T22:27:22.253+0700
SCRUM-37 | [OPERATE-5] Write blameless postmortem and file follow-up tickets | Story | Idea | Low | Dev Ops | owner-devops, phase-5, role-sre, sprint-5 | SCRUM Sprint 4 (future) | SCRUM-9 - [Phase 5] Incident Response and Error-Budget Policy | 3 | As the SRE-hat-wearer, I want to write a blameless postmortem for the triggered incident and file the resulting follow-up work so that the exercise produces durable improvement, not just a war story. | - Given the incident is resolved, when I write the postmortem, then it covers timeline, root cause, impact, and what went well/poorly — with no blame language about "who" caused it. - Given the postmortem identifies gaps, when I finish it, then each gap becomes a filed Jira ticket, not just a bullet point that gets forgotten. - Given the postmortem is complete, when I review it later, then it's specific enough to actually prevent a repeat, not generic ("improve monitoring"). Test Scenarios - Review the postmortem draft for any blame-attributing language — rewrite if found. - Cross-check that every "action item" in the postmortem has a corresponding Jira ticket. - Six months from now (hypothetically), read the postmortem cold — confirm it's still understandable without this conversation's context. | 2026-08-13T20:27:35.434+0700 | 2026-09-06T16:50:12.164+0700
SCRUM-38 | [OPERATE-5] Practice toggle-gated rollback without a redeploy | Story | Idea | Low | dev3 | owner-dev3, phase-5, role-devops, sprint-3 | SCRUM Sprint 4 (future) | SCRUM-9 - [Phase 5] Incident Response and Error-Budget Policy | 5 | As the DevOps-hat-wearer, I want to ship a change behind a feature toggle and then disable it without a redeploy so that rollback speed during an incident is proven, not theoretical (Principle X). | - Given a non-trivial change ships, when I check it, then it's behind a feature toggle with a named owner and a recorded removal date. - Given the toggle is flipped off, when I observe the system, then the change is fully disabled with no code deploy or pod restart required. - Given the toggle-gated change touches the database, when I check the migration, then it's backward compatible with the previous version (expand/contract, not destructive). Test Scenarios - Ship a small feature behind a toggle, flip it off, and time how long full rollback takes — should be seconds, not a deploy cycle. - Run both toggle states simultaneously against the same DB schema — confirm no breakage either way. - Check the toggle registry for a name, owner, and removal date on this toggle — confirm none are missing. | 2026-08-13T20:27:41.798+0700 | 2026-09-06T16:50:08.542+0700
SCRUM-39 | [OPERATE-5] Run a quarterly-style constitutional compliance review | Story | Idea | Low | QA | owner-qa, phase-5, role-po, sprint-5 | SCRUM Sprint 4 (future) | SCRUM-9 - [Phase 5] Incident Response and Error-Budget Policy | 5 | As the Product Owner, I want to run a compliance review of the live system against every principle in the constitution so that drift is caught deliberately rather than discovered by accident (Governance section). | - Given the constitution's 10 principles, when I review the system, then each principle is checked off with evidence (not just "looks fine"), or a documented, time-bounded deviation is recorded. - Given a deviation is found, when I document it, then it includes the justification and the simpler alternative that was rejected, per the Governance section. - Given the review completes, when I file findings, then non-compliant items become tracked Jira tickets, not just notes. Test Scenarios - Walk through Principles I–X one by one against the live system and record pass/fail/deviation for each. - Pick one deviation (if any) and confirm it has a documented justification and a time bound. - Confirm every "fail" from the review has a corresponding Jira ticket filed. | 2026-08-13T20:27:47.707+0700 | 2026-09-06T16:50:15.702+0700